## Risks
MYES Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 10.04.2021 | A passenger may make excessive reservations for a certain trip | A passenger may reserve all the seats to a certain trip so other passengers cannot make any reservations. Unless actually bought, reserving all seats may block the bus and result in business losses for bus companies. | Business | 4 | 20% | 0.8 | Analyst | Avoid
2 | 10.04.2021 | Developer error in the CRUD operations. | Errorneous actions may occur on the database and data integrity may get damaged. | Technical | 5 | 10% | 0.5 | Development Team | Mitigate
3 | 10.04.2021 | Having trouble on accessing servers. | There may be a problem which might cause accounts to be not reachable. | Technical | 7 | 5% | 0.35 | Development Team | Accept
4 | 10.04.2021 | Inaccurate budget estimation | Due to the inaccurate budget estimation, the project may run out of budget | Budget | 6 | 40% | 2.4 | Project Manager | Avoid
5 | 10.04.2021 | Security risk | System might be hacked and private and personal data or information may be exposed to malicious third parties | Technical | 8 | 15% | 1.2 | Development Team | Mitigate
6 | 10.04.2021 | Ambiguous project design and deliverables | Because of problems in scope definition and scheduling, there can be ambigous or incomplete project designs and deliverables | Schedule | 8 | 30% | 2.4 | Project Manager | Mitigate
7 | 10.04.2021 | Loss of the project team members | Team members may have health problems or may leave the job. | Human Resource | 6 | 40% | 2.4 | Project Manager | Transfer
8 | 10.04.2021 | Payment vendor error | Payment vendor is an external actor and in case of an error MYES customers will not able to pay for their tickets. There should be alternative payment methods. | Business | 5 | 5% | 0.25 | Analyst | Mitigate
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
| Risk #1 | Handled in Iteration2 | It is addressed in system-wide requirement documents by adding the business rule 'Reservation004'
| Risk #2 | Handled in Iteration2 | In Django models, all the CRUD operations constraints are defined and Django framework is taking care of these contraints for us. Since the most of the user forms are created automatically from the django models. It became very hard for users to make errornous operations in CRUD operations