## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Preparing Vision Document | 1 | 4 | Completed | 1 | Serdar Mumcu | 0 | 4 | Vision Template
Preparing Glossary Document | 2 | 3 | Completed | 1 | Serdar Mumcu | 0 | 3 | None
Preparing Iteration 1 Plan | 1 | 3 | Completed | 1 | Serdar Mumcu | 0 | 3 | Iteration Plan Template
Creating the Project Plan | 1 | 8 | Completed | 1 | Serdar Mumcu | 0 | 8 | Project Plan Template
System-wide Req. Specification | 1 | 8 | Completed | 1 | Mustafa Ilıkkan | 0 | 8 | System-wide Req. Spec. Template
All Use-cases in Brief Format | 1 | 8 | Completed | 1 | Eren Erol - Yiğit Erkal | 0 | 8 | Use-case Specification Template
UC1 in Fully Dressed Format | 1 | 2 | Completed | 1 | Eren Erol - Yiğit Erkal | 0 | 2 | Use-case Specification Template
UC3 in Fully Dressed Format | 1 | 2 | Completed | 1 | Eren Erol - Yiğit Erkal | 0 | 2 | Use-case Specification Template
UC4 in Fully Dressed Format | 1 | 2 | Completed | 1 | Eren Erol - Yiğit Erkal | 0 | 2 | Use-case Specification Template
UC5 in Fully Dressed Format | 1 | 2 | Completed | 1 | Eren Erol - Yiğit Erkal | 0 | 2 | Use-case Specification Template
Creating a Risk List | 1 | 5 | Completed | 1 | Eren Erol - Yiğit Erkal | 0 | 5 | Risk List Template
Creating Work Items List | 1 | 3 | Completed | 1 | Serdar Mumcu | 0 | 3 | Work Items List Template
Creating (First Elaboration) Iteration 2 Plan | 1 | 3 | Completed | 1 | Serdar Mumcu | 0 | 3 | Iteration Plan Template
53
Establishing Development Environment | 1 | 5 | Not Started | 2 | Serdar Mumcu | 5 | 0 | None
Opening a Cloud Account | 1 | 3 | Not Started | 2 | Serdar Mumcu | 3 | 0 | None
Updating Project Plan | 2 | 2 | Not Started | 2 | Serdar Mumcu | 2 | 0 | Project Plan Template
Updating Iteration 2 Plan | 2 | 1 | Not Started | 2 | Serdar Mumcu | 1 | 0 | Iteration Plan Template
Creating Architectural Notebook | 1 | 8 | Not Started | 2 | Mustafa Ilıkkan | 8 | 0 | Architecture Notebook Template
UC2 in Fully Dressed Format | 1 | 2 | Not Started | 2 | Eren Erol - Yiğit Erkal | 2 | 0 | Use-case Specification Template
UC8 in Fully Dressed Format | 1 | 1 | Not Started | 2 | Eren Erol - Yiğit Erkal | 1 | 0 | Use-case Specification Template
UC9 in Fully Dressed Format | 1 | 1 | Not Started | 2 | Eren Erol - Yiğit Erkal | 1 | 0 | Use-case Specification Template
UC10 in Fully Dressed Format | 1 | 1 | Not Started | 2 | Eren Erol - Yiğit Erkal | 1 | 0 | Use-case Specification Template
Preparing Initial Design Document | 1 | 8 | Not Started | 2 | Serdar Mumcu | 8 | 0 | Design Template
Creating Test Related Documents | 1 | 8 | Not Started | 2 | Eren Erol - Yiğit Erkal | 8 | 0 | Test Cases Template
Handling of Risk #1 | 2 | 3 | Not Started | 2 | Eren Erol - Yiğit Erkal | 3 | 0 | None
Handling of Risk #2 | 2 | 3 | Not Started | 2 | Serdar Mumcu | 3 | 0 | None
Implementation of UC1 | 1 | 3 | Not Started | 2 | Serdar Mumcu | 3 | 0 | None
Implementation of UC3 | 1 | 8 | Not Started | 2 | Mustafa Ilıkkan | 8 | 0 | None
Implementation of UC4 | 1 | 8 | Not Started | 2 | Eren Erol | 8 | 0 | None
Implementation of UC5 | 1 | 8 | Not Started | 2 | Eren Erol | 8 | 0 | None
Testing Partial Software | 1 | 3 | Not Started | 2 | Yiğit Erkal | 3 | 0 | None
Deploying Partial Software | 1 | 3 | Not Started | 2 | Serdar Mumcu | 3 | 0 | None
Creating (Second Elaboration) Iteration 3 Plan | 1 | 3 | Not Started | 2 | Serdar Mumcu | 3 | 0 | Iteration Plan Template
82
Revising Current Iteration Plan | 1 | 1 | Not Started | 3 | Serdar Mumcu | 1 | 0 | Iteration Plan Template
Preparing Next Iteration Plan | 1 | 3 | Not Started | 3 | Serdar Mumcu | 3 | 0 | Iteration Plan Template
Finalizing the Architecture Document | 1 | 3 | Not Started | 3 | Mustafa Ilıkkan | 3 | 0 | Architecture Notebook Template
Writing remaining use-cases in a fully dressed format | 1 | 3 | Not Started | 3 | Eren Erol - Yiğit Erkal | 3 | 0 | Use-case Specification Template
Writing more test cases | 1 | 5 | Not Started | 3 | Eren Erol - Yiğit Erkal | 5 | 0 | Test Cases Template
Handling of Risk #5 | 2 | 3 | Not Started | 3 | Mustafa Ilıkkan | 3 | 0 | None
Handling of Risk #6 | 2 | 3 | Not Started | 3 | Serdar Mumcu | 3 | 0 | None
Implementing UC2, UC8, UC9 and UC11 | 1 | 32 | Not Started | 3 | Every Team Member | 32 | 0 | None
Testing Partial Software | 1 | 3 | Not Started | 3 | Yiğit Erkal | 3 | 0 | None
Deploying 2nd Running Partial Software to the Cloud P. | 1 | 3 | Not Started | 3 | Serdar Mumcu | 3 | 0 | None
59
Revising Current Iteration Plan | 1 | 1 | Not Started | 4 | Serdar Mumcu | 1 | 0 | Iteration Plan Template
Implementing UC7 and UC12 | 1 | 21 | Not Started | 4 | Every Team Member | 21 | 0 | None
Testing First Release | 1 | 5 | Not Started | 4 | Yiğit Erkal | 5 | 0 | None
Handling of Risk #4 | 1 | 3 | Not Started | 4 | Serdar Mumcu | 3 | 0 | None
Handling of Risk #8 | 1 | 3 | Not Started | 4 | Mustafa Ilıkkan | 3 | 0 | None
Deploying First Release to the Cloud Platform | 1 | 3 | Not Started | 4 | Serdar Mumcu | 3 | 0 | None
Finalizing all artifacts | 1 | 34 | Not Started | 4 | Every Team Member | 34 | 0 | None
70