## Risks
MYES Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 10.04.2021 | A passenger may make excessive reservations for a certain trip | A passenger may reserve all the seats to a certain trip so other passengers cannot make any reservations. Unless actually bought, reserving all seats may block the bus and result in business losses for bus companies. | Business | 4 | 20% | 0.8 | Analyst | Avoid
2 | 10.04.2021 | Developer error in the CRUD operations. | Errorneous actions may occur on the database and data integrity may get damaged. | Technical | 5 | 10% | 0.5 | Development Team | Mitigate
3 | 10.04.2021 | Having trouble on accessing servers. | There may be a problem which might cause accounts to be not reachable. | Technical | 7 | 5% | 0.35 | Development Team | Accept
4 | 10.04.2021 | Inaccurate budget estimation | Due to the inaccurate budget estimation, the project may run out of budget | Budget | 6 | 40% | 2.4 | Project Manager | Avoid
5 | 10.04.2021 | Security risk | System might be hacked and private and personal data or information may be exposed to malicious third parties | Technical | 8 | 15% | 1.2 | Development Team | Mitigate
6 | 10.04.2021 | Ambiguous project design and deliverables | Because of problems in scope definition and scheduling, there can be ambigous or incomplete project designs and deliverables | Schedule | 8 | 30% | 2.4 | Project Manager | Mitigate
7 | 10.04.2021 | Loss of the project team members | Team members may have health problems or may leave the job. | Human Resource | 6 | 40% | 2.4 | Project Manager | Transfer
8 | 10.04.2021 | Payment vendor error | Payment vendor is an external actor and in case of an error MYES customers will not able to pay for their tickets. There should be alternative payment methods. | Business | 5 | 5% | 0.25 | Analyst | Mitigate
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0